## 2013 Mission Planner
2013-01-02 | Travel Day | Travel Day | Travel Day |  | yellow highlight = previous days
| TL Name | TL name
2013-01-03 | Location Segment ID Mission type status | E.G. | North Bay NB01-012 SIR Passed
2013-01-04 |  |  |  | Travel Day
2013-01-05
2013-01-06
2013-01-07
2013-01-08
2013-01-09
2013-01-10
2013-01-11
2013-01-12
2013-01-13
2013-01-14
2013-01-15
2013-01-16
2013-01-17
2013-01-18
2013-01-19
2013-01-20
2013-01-21
2013-01-22
2013-01-23
2013-01-24
2013-01-25
2013-01-26
2013-01-27
2013-01-28
2013-01-29
2013-01-30
2013-01-31

## July-Dec 2012
blue = Fourchon/green = Venice | Team 1 | Team 2 | Team 3 | Team 4 | Team 5
2012-07-01 | Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25)
Graham MacDonald
2012-07-02 | West Timbalier Beach Profiles finish June | Trinity Island- Beach Profiles 6 and 7 for June/ Whiskey Island- reset front and back stake of profile #6
| Kulp | Graham MacDonald
2012-07-03 | Cancelled due to high water levels- Office work | Cancelled due to high water levels- Office work
| Kulp | Graham MacDonald
2012-07-04 | 4th of July Holiday
Kulp
2012-07-05 | Plaquemines N Barataria Bay bagasse and PM- completed 1 site then cut early due to Wx | Plaquemines N Barataria Bay bagasse and PM- completed 1 site then cut early due to Wx
| Kulp | Ramsey
2012-07-06 | Plaquemines N Barataria Bay bagasse and PM | Plaquemines N Barataria Bay bagasse and PM | Grand Terre 2- Beach Profiles for June- nesting in zones 1,7,8 &9
| Kulp | Ramsey | FitzGerald
2012-07-07 | Grand Isle- Beach Profiles for July | Grand Isle- Beach Profiles for July | Elmer's Island Beach Profiles for July | N Barataria Bay <.7 until noon
| Kulp | Ramsey | FitzGerald
2012-07-08 | Canceled due to Thunderstorms OLS-N Barataria Bagasse Treatment | Canceled due to Thunderstorms N Barataria (S4-032.r.1) SIR-1- LAPL01-034-10 (gap b/t zones J & M- includes 2 set asides) | Canceled due to Thunderstorms Casse-Tete & Calumet Islands PM- sites #35-40 (Casse-Tete) & site #43 (Calumet) | N Barataria Bay <.7 all day
| Kulp | Ramsey | FitzGerald
2012-07-09 | Canceled due to thunderstorms-N Barataria (S4-032.r.1) SCAT Mon-LAPL01-052-10 (Zone A)-past 30 days but have made multiple attempts | Canceled due to thunderstorms-N Barataria (S4-032.r.1) SCAT Mon- LAPL01-034-50 (Zone L-includes 3 set asides) | Canceled due to thunderstorms-Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25)- | Canceled due to thunderstorms N Barataria (S4-032.r.1) SCAT Mon- LAPL01-052-30 (Zone B- North)- past 30 days but have made multiple attempts
| Kulp | Ramsey | FitzGerald | Chapman- arrives in NOLA at 0735
2012-07-10 | Canceled due to thunderstorms West Timbalier (S4-027.r.2) SIR-2- LATB04-010-10 (zones 7, 8, and 9) SCAT Mon- LATB04-009-10 & LALF01-036-20 | Canceled due to thunderstorms N Barataria (S4-032.r.1) SIR-1- LAPL01-034-10 (gap b/t zones J & M- includes 2 set asides)- survey with team #4 & SCAT Mon (3)-LAPL01-052-10 (Zone A) | Meeting- OSAT-3 | Canceled due to thunderstorms N Barataria (S4-032.r.1) SIR-1- LAPL01-034-10 (gap b/t zones J & M- includes 2 set asides)-survey with team #2 & SCAT Mon (3)- LAPL01-052-30 (Zone B- North)
| Grenon | Ramsey | FitzGerald | Chapman
2012-07-11 | Canceled due to Thunderstorms Whiskey Island (S4-024): SIR-2 LATB03-004-10 (Zones 1-4); LATB03-005-10 (Zones 4-8); LATB03-006-10 (Zones 8 and 9) | Drum Bay (S4-007) SIR-2- LASB06-002-10 & Turtle Pen Isle (S4-038)SIR-1 (partial)- LASB05-017-10 (TPI) | South Pass (S3-003.r.7) SCAT Mon- LAPL06-010-20 SIR-2- LAPL06-001-35 | N Barataria (S4-032.r.1) SIR-1- LAPL01-034-10 (gap b/t zones J & M- includes 2 set asides)- & SIR-2- LAPL01-053-60 (zone G) and LAPL01-053-70 (zone C) | Isle Dernieres requires 48 hr notice
| Grenon | Ramsey | FitzGerald (TA-if Ed not here) | Chapman
2012-07-12 | Trinity Island (S4-023.r.1)SIR-2 LATB03-004-10, LATB03-005-10 & LATB03-006-10- few extra boats for STERA/VMP (Matt D) SCAT Mon- LATB04-002-10 | Creole Gap Key (S4-038)-SCAT Mon- LASB07-010-10 & LASB07-012-10 | South Pass (S3-003.r.7) SCAT Mon- LAPL06-010-20 SIR-2- LAPL06-001-35 | N Barataria (S4-032.r.1) SIR-2- LAPL01-053-60 (zone G) and LAPL01-053-70 (zone C)-must finish by end of day or will get kicked back toSCAT MON/
| Grenon | Ramsey | FitzGerald (TA- if Ed not here) | Chapman
2012-07-13 | Canceled due to Thunderstorms West Timbalier (S4-027.r.2) SIR-2- LATB04-010-10 (zones 7, 8, and 9) LATB04-004-10 (zones 9-12) SCAT Mon- LATB04-010-20, LATB04-009-10 & LALF01-036-20 | Canceled due to Thunderstorms Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25) | South Pass <.5 @ noon
| Grenon | Chapman
2012-07-14 | West Timbalier (S4-027.r.2) SIR-2-LATB04-004-10 (zones 9-12)- did not pass | Tide <.5 starting at 3pm
Grenon
2012-07-15 | Canceled at dock due to Thunderstorms SW Pass (S4-030.r.1)SCAT Mon- LAPL05-009-10 | Grand Terre 3- Beach Profiles for July and PM site #'s 25 & 30 | S Pass <.5 @ noon
| Grenon | MacDonald
2012-07-16 | Fourchon Beach- Beach Profiles for July- Profile sites 3 - 16. | Grand Terre 1- Beach profiles for July- did profiles 12-6 then cut short due to Thunderstorms
| Kulp | MacDonald
2012-07-17 | SW Pass (S4-030.r.1) SCAT Mon- LAPL05-009-10 | Office- profile data | South Pass (S3-003.r.7)SIR-2- LAPL06-010-20 & LAPL06-001-35 SIR-1- LAPL06-002-10 SCAT Mon- LAPL06-010-05 & LAPL07-004-10
| Kulp | MacDonald | FitzGerald
2012-07-18 | SW Pass (S4-030.r.1) SIR-2- LAPL05-009-10 | Canceled due to Water Spouts Casse-Tete & Calumet Islands PM- sites #35-40 (Casse-Tete) & site #43 (Calumet) | South Pass (S3-003.r.7) SCAT Mon- LAPL06-001-35
| Kulp | MacDonald | FitzGerald
2012-07-19 | Canceled due to Thunderstorms at dock West Timbalier Beach Profiles 3-5 PM site #'s 42,49 &51 | Canceled due to Thunderstorms at dock Grand Terre 1- Beach Profiles for July- finish 1-6 | OLS- Elmer's Island (no state or FED required)
| Kulp | MacDonald | FitzGerald
2012-07-20 | Canceled in field due to high water levels Bay Jimmy PM site #'s 5, 6,10,11,13,14 & 24 | Canceled in field due to high water levels Bay Jimmy PM site #'s 5, 6,10,11,13,14 & 24 | Canceled due to Thunderstorms Whiskey Island- Beach Profiles for July | Canceled due to Thunderstorms Grand Terre 2- Beach Profiles for July. Nesting in Zones 7-10
| Kulp | MacDonald | Ramsey | FitzGerald
2012-07-21 | Canceled due to water spout and rough seas (able to do 1 profile) Trinity Island- Beach Profiles for July | Office Day- Profile Data | Elmer's Island- Beach Profiles for July #'s 7-12 and reset stake #1 | Canceled due to high water levels and rough seas Casse-Tete & Calumet Islands PM- sites #35, 39 & 40 (Casse-Tete) & site #43 (Calumet)
| Kulp | MacDonald | Ramsey | FitzGerald
2012-07-22 | Canceled due to high water levels N Barataria (S4-032.r.1) SIR-2- LAPL01-052-30 (Zone B- North) & LAPL01-053-70 (zone C) | Canceled due to high water levels N Barataria (S4-032.r.1) SIR-2- LAPL01-052-10 (Zone A) & CAT Mon- LAPL01-034-50 (Zone L-includes 3 set asides) | Canceled due to high water levels N Barataria (S4-032.r.1) SCAT Mon- LAPL01-029-20 (incl. Zone U) & SCAT Mon- LAPL01-036-30 (incl. Zone AB) | N Barataria <.7 till 11am
| Kulp | Ramsey | FitzGerald
2012-07-23 | N Barataria (S4-032.r.1) SIR-1- LAPL01-029-10 (Zones P,Q,S & V) | Canceled due to high water levels N Barataria (S4-032.r.1) SCAT Mon- LAPL01-040-10 (zone AC) & SCAT Mon- LAPL01-034-50 (Zone L-includes 3 set asides)-if not done on 7/22/12 | Canceled due to high water levels N Barataria (S4-032.r.1) SCAT Mon- LAPL01-036-30 (Zone AB)-if not done on prior day & SCAT Mon- LAPL01-029-20 (Zone U) | Canceled due to high water levels N Barataria (S4-032.r.1) SIR-1- LAPL01-035-10 & LAPL01-035-40 (Both are Zone X) | OLS- KeelBoat Pass
| Kulp | Kroninger | FitzGerald | Chapman- p/u from MSY @ 730 | Ramsey
2012-07-24 | N Barataria (S4-032.r.1) SIR-2- LAPL01-052-10 (Zone A)-did 3/4 of segment & SIR-2- LAPL01-052-30 (Zone B- North) | Canceled due to high water levels Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25) / did Grand Terre 1 - Beach Profiles 1-6 instead- verified w/parish & state | Canceled due to high water levels N Barataria (S4-032.r.1) SIR-2- LAPL01-053-70 (Zone C) | OLS- KeelBoat Pass |  | UTV Maintenance Matt D
| Kulp | Kroninger | Chapman | Ramsey
2012-07-25 | Trinity Island (S4-023.r.1): SIR-2 LATB03-007-10 & LATB03-008-10 SCAT Mon- LATB04-006-10 | Whiskey Island (S4-024): SCAT MON- LATB03-005-10 (Zones 4-8) did half of segment; LATB03-006-10 (Zones 8 and 9) | West Timbalier (S4-027.r.2) SIR-2- LATB04-010-10 (zones 7, 8, and 9) SCAT Mon- LATB04-009-10 & LALF01-036-20/ PM site #'s 42,49 &51 completed SCAT Mon on LATB04-010-20 | Drum Bay (S4-007) partial SIR-2- LASB06-002-10- cut short due to Thunderstorms | GI Tarpon Rodeo
| Graham MacDonald | Kroninger | Chapman | Ramsey
2012-07-26 | Canceled due to rough seas Whiskey Island (S4-024): SIR-2 LATB03-004-10 (Zones 1-4); SCAT MON- LATB03-005-10 (Zones 4-8) half of segment; LATB03-006-10 (Zones 8 and 9) | Drum Bay (S4-007) partial SIR-2- LASB06-002-10- cut short due to Thunderstorms/ Turtle Pen Isle (S4-038) partial SIR-1- LASB05-017-10 | Creole Gap Key (S4-038)-SCAT Mon- LASB07-010-10-meets SCCP endpts & LASB07-012-10- ALARP | Canceled night before due to fishing rodeo Casse-Tete Island (S4-034.r.1) SCAT Mon- LALF01-045-10 (zones 2 & 3) & Brush Island (S4-037.r.1) SIR-1- LALF01-037-10 Casse-Tete Island (S4-037.r.1) SIR-1- LALF01-037-10 (zone 1) PIST-LALF01-044-10 (zones 3,4,5 & 6) | GI Tarpon Rodeo
| Graham MacDonald | Kroninger | Ramsey | Kulp
2012-07-27 | Whiskey Island(S4-024): SIR-2 LATB03-004-10 (Zones 1-4); SCAT MON- LATB03-005-10 (Zones 4-8) half of segment; Beach Profiles for July | Canceled due to Thunderstorms Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25)/ PIST- LAPL01-002-10 (Zone 23) | Canceled day prior due to fishing rodeo South Pass (S3-003.r.7) SIR-2- LAPL06-010-20 (water levels) SIR-2-Garden Island- LAPL07-004-10 SCAT Mon- LAPL06-010-05 SIR-1- LAPL06-002-10 | GI Tarpon Rodeo
| Graham MacDonald | Kroninger | Ramsey
2012-07-28 | Canceled in field due to Thunderstorms Trinity Island- Beach Profiles for July | GI Tarpon Rodeo
Graham MacDonald
2012-07-29 | cont Whiskey Island(S4-024): SIR-2 LATB03-004-10 (Zones 1-4); SCAT MON- LATB03-005-10 (Zones 4-8) half of segment | GI Tarpon Rodeo
Graham MacDonald
2012-07-30 | Trinity Island-finish Beach Profiles for July | Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25)/ PIST- Zone 23 | South Pass (S3-003.r.7) SIR-2- LAPL06-010-20 (water levels) SIR-2-Garden Island- LAPL07-004-10 (finished 3/4 of Garden Island but airboat broke down and couldn't finish rest) SCAT Mon- LAPL06-010-05 SIR-1- LAPL06-002-10
| Graham MacDonald | Ramsey | FitzGerald
2012-07-31 | West Timbalier Island- Beach Profiles 3-5 for August and PM site #42 | Grand Terre 2- Beach Profiles for August | Casse-Tete and Calumet Island- PM site #'s 35, 39, 40 & 43
| Graham MacDonald | FitzGerald | Ramsey
2012-08-01 | Grand Isle- Beach Profiles for August | Grand Isle- Beach Profiles for August
| Graham MacDonald | FitzGerald
2012-08-02 | Canceled- NO MORE PROFILES/PM Trinity Island- finish Beach Profiles for August
Graham MacDonald
2012-08-03 | Office
Grenon
2012-08-04 | OPS support- Fourchon Breach pics
Grenon
2012-08-05 | Canceled due to high water levels N Barataria (S4-032.r.1)SCAT Mon- LAPL01-051-10 and LAPL01-053-10 (F) | Canceled due to high water levels N Barataria (S4-032.r.1) SCAT Mon(2) - LAPL01-034-50 (L) | N Barataria (S4-032.r.1) SCAT Mon- LAPL01-036-10 (R,T,Y,Z)- completed partial | N Barataria- Tide <.7 until 1300
| Nelson | Grenon | Kulp w/SOSC Dan Lambert
2012-08-06 | Canceled due to high water levels and thunderstorms N Barataria (S4-032.r.1) SCAT Mon 2- LAPL01-036-30 (AB) | Canceled due to high water levels and thunderstorms N Barataria (S4-032.r.1) SCAT Mon (2)- LAPL01-053-30 (zone D,E) | Canceled due to high water levels and thunderstorms N Barataria (S4-032.r.1) SIR-2- LAPL01-053-70 (zone C)
| Nelson | Grenon | Kulp
2012-08-07 | Fort Livingston for Arch Support | Grand Terre 2 (S4-020.r.1) SIR-1- LAPL01-002-10 (zones 16-25) | N Barataria (S4-032.r.1) SCAT Mon- LAPL01-036-10 (R,T,Y,Z)- completed partial from 8/5/12 SIR-1 LAPL01-035-10-started and LAPL01-035-40 (both are Zone X) | N Barataria (S4-032.r.1) SIR-2- LAPL01-052-10 (zone A) and/or SIR-1- LAPL01-029-10 - (P,Q,S,V) | Eric Schneider coming to Houma
| Nelson | Grenon | Kulp | Ramsey
2012-08-08 | Calumet Island (S4-035) SCAT Mon- LALF01-044-30-ready for SIR2 & Brush Island (S4-037.r.1) SIR-1- LALF01-037-10- not able to get to Casse-Tete Island (S4-037.r.1) PIST-LALF01-044-10- mitigated will have to re-schedule PIST | South Pass (S3-003.r.7) SIR-2- LAPL07-004-10 & LAPL06-010-20 SCAT Mon- LAPL06-010-05-ready for SIR-2 SIR-1- LAPL06-002-10- completed front side but not back side | Canceled due to Thunderstorms before leaving dock KeelBoat Pass (S4-038.r.1) PIST- LASB05-014-20 & LASB05-015-10 (zone 3)
| Nelson | Kulp | Ramsey
2012-08-09 | Canceled due to rough seas/wind Whiskey Island (S4-024) SIR-2-LATB03-005-10 & LATB03-006-10 | Canceled due to rough seas and tide falling West Timbalier (S4-027.r.2) SIR-2- LATB04-010-20 & LATB04-010-10 & SCAT Mon- LALF01-036-20 | Canceled due to thunderstorms KeelBoat Pass (S4-038.r.1) PIST- LASB05-014-20 & LASB05-015-10 (zone 3)
| Nelson | Kulp | Ramsey
2012-08-10 | Wisner Meeting- per request GH | Trinity Island (S4-023.r.1) SIR-2- LATB04-006-10 & SIR-1- LATB04-001-20 & LATB04-007-10 & PIST- LATB04-001-10-completed partial PIST on zone 5 | Canceled due to thunderstorms Creole Gap Key (S4-038) SIR-2-LASB07-010-10 & LASB07-012-10
| FitzGerald | Kulp | Ramsey
2012-08-11 | Canceled due to thunderstorms South Pass (S3-003.r.7) SIR-2- LAPL07-004-10 & LAPL06-010-20 SIR-1- LAPL06-002-10- complete back side | Drum Bay (S4-007) partial SIR-2- LASB06-002-10 | N Barataria (S4-032.r.1) SIR-2- LAPL01-052-10 (zone A)-completed partial from mitigation on 8/7/12 | Last day of N Barataria Bay (tides) starts @ 1400
| FitzGerald | Kulp | Ramsey
2012-08-12 | South Pass (S3-003.r.7) SIR-2- LAPL07-004-10 (completed) & LAPL06-010-20 SIR-2- LAPL06-010-05 | SW Pass (S4-030.r.1) SIR-2- LAPL05-009-10 | Whiskey Island(S4-024) SIR-2-LATB03-005-10 & LATB03-006-10- completed all of LATB03-005-10 and partial of LATB03-006-10
| FitzGerald | Kulp | Ramsey
2012-08-13 | South Pass- (S3-003.r.7) SIR-2- LAPL06-010-20 & LAPL06-010-05 SIR-1- LAPL06-002-10 | West Timbalier (S4-027.r.2) SIR-2- LATB04-010-20- tide <.5 @ 3pm
| FitzGerald | Kulp
2012-08-14 | Grand Terre 2- beach recon | Grand Terre 2- beach recon | Tides +.5 majority of day
| FitzGerald | MacDonald
2012-08-15 | South Pass- (S3-003.r.7) SIR-2- LAPL06-001-35 | West Timbalier (S4-027.r.2) cont SIR-2- LATB04-010-20- passed w/o doing last 2 dredge spoils
| FitzGerald | MacDonald
2012-08-16 | Elmer's Island (S4-025) SIR-1- LAJF01-004-20
MacDonald
2012-08-17 | Office- Profile Data | High Tides
MacDonald
2012-08-18 | Office- Profile Data | High Tides
MacDonald
2012-08-19 | Office- Binder Work | Canceled due to Thunderstorms N Barataria Bagasse Recon | Canceled due to Thunderstorms N Barataria Bagasse Recon | N Barataria <.8 until noon
| Kroninger | MacDonald | Kulp
2012-08-20 | Office- Binder Work | Canceled due to Thunderstorms/ High Water Levels N Barataria (S4-032.r.1)SIR-2- LAPL01-051-10 and LAPL01-053-10 (F) | Canceled due to Thunderstorms West Timbalier (S4-027.r.2) PIST- LATB04-004-10 (Zones 10 & 11) | Canceled due to Thunderstorms/ High Water Levels N Barataria (S4-032.r.1) SCAT Mon(2) - LAPL01-034-50 (L) | Canceled due to Thunderstorms N Barataria Bagasse Recon | N Barataria Bay tides get good again
| Kroninger | MacDonald | FitzGerald | Chapman | Kulp/ MECS Richardson | Debra gets in
2012-08-21 | Casse-Tete Island (S4-034.r.1) SCAT Mon- LALF01-045-10 (zones 2 & 3)-did not pass/recommending bagasse tx | N Barataria (S4-032.r.1) SCAT Mon 2- LAPL01-036-30 (AB)- passed + Bagasse Recon- looked at site H | Trinity Island (S4-023.r.1) PIST- LATB04-001-10 (only zones 6 and 7)- did not pass / West Timbalier (S4-027.r.2) PIST- LATB04-004-10 (Zones 10 & 11)- did not pass | N Barataria (S4-032.r.1)SCAT Mon (2)- LAPL01-053-30 (zone D,E)- did not pass+ Bagasse Recon
| Kroninger | Ramsey | FitzGerald | Chapman
2012-08-22 | Calumet Island (S4-035) SIR-2 LALF01-044-30- did not survey due to time / Casse-Tete Island (S4-037.r.1) PIST(2)-LALF01-044-10- passed | KeelBoat Pass (S4-038.r.1) PIST- LASB05-014-20- passed & LASB05-015-10 (zone 3)- did not pass | West Timbalier (S4-027.r.2) SIR-2- LATB04-010-20- did not survey due to segment hold & & SCAT Mon- LALF01-036-20- did not survey , LATB04-009-10- passed & LATB04-010-10- passed | N Barataria (S4-032.r.1)SIR-2- LAPL01-051-10 and LAPL01-053-10 (F)- not done due to bagasse tx at Zone H+ OPS Bagasse Trials | Canceled due to flight delays Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25)
| Kroninger | Ramsey | FitzGerald | Chapman | Graham MacDonald
2012-08-23 | Whiskey Island (S4-024) partial SIR-2- LATB03-006-10 (NE corner needs tide = .3-.5)-passed | Creole Gap Key (S4-038) SIR-2-LASB07-010-10 & LASB07-012-10 | South Pass (S3-003.r.7) SIR-2- LAPL06-010-20 partial SIR-2- LAPL07-004-10 partial SIR-1- LAPL06-002-10- backside | N Barataria (S4-032.r.1) SIR-2- LAPL01-051-10 and LAPL01-053-10 (F)+ Bagasse Trials / SCAT Mon- LAPL01-053-70 (zone C)- pushed back till 9/7/12 due to Zone F taking higher priority | Brush Island (S4-037.r.1) SIR-1- LALF01-037-10 (zone 1)-passed
| Kroninger | Ramsey | FitzGerald | Chapman | Graham MacDonald
2012-08-24 | Mission Canceled Due to Rough Seas Creole Gap Key (S4-038) SIR-2-LASB07-010-10- encounterd black skimmer nest ~20 chicks & LASB07-012-10-did walking portion only due to airboat breaking down | Elmer's Island (S4-025) PIST- LAJF01-004-20 (portion), LAJF01-004-60, LAJF01-004-40 (portion), LAJF01-002-10, LAJF01-001-10- completed zones 1-4 | N Barataria (S4-032.r.1) SIR-1 LAPL01-035-10 and LAPL01-035-40 (both are Zone X) & SCAT Mon -LAPL01-053-70 (zone C) - did not get to surveys but looked at zones N, G & D for bagasse tx | Mission Canceled Due to Lightning Trinity Island (S4-023.r.1) SIR-2- LATB04-006-10 SIR-1- LATB04-001-20 & LATB04-007-10
| Ramsey | FitzGerald | Chapman | Graham MacDonald
2012-08-25 | Canceled due to Hurricane Isaac Bay Chaland- PIST- LAPL01-003-10 & LAPL01-005-30 (portion) | Canceled due to Hurricane Isaac Grand Terre 1- PIST- LAJF01-016-20 & LAJF01-017-10 (zones 1-6) + pre-storm beach profiles | Canceled due to Hurricane Isaac Fourchon Beach (S4-017) PIST- LALF02-006-10 (zones 8 & 9) + pre-storm beach profiles | Last day of N Barataria Bay (tides) starts @ 1330
| Ramsey | FitzGerald | Graham MacDonald
2012-08-26 | Canceled due to Hurricane Isaac Calumet Island (S4-035) SIR-2 LALF01-044-30 | Canceled due to Hurricane Isaac West Timbalier (S4-027.r.2) SCAT Mon- LALF01-036-20 + pre-storm beach profiles | Canceled due to Hurricane Isaac Grand Terre 2 (S4-020.r.1) SCAT Mon- LAPL01-002-10 (zones 16-25) + pre-storm beach profiles
| Ramsey | FitzGerald | Graham MacDonald
2012-08-27 | Hurricane Isaac | Hurricane Isaac | Hurricane Isaac | Tides <.5 at Timbalier @ 1500/ Tide <.5 at Caminada pass starting at 1500
| Kulp | Graham MacDonald | FitzGerald
2012-08-28 | Hurricane Isaac
Graham MacDonald
2012-08-29 | Hurricane Isaac | High Tides
Graham MacDonald
2012-08-30 | Hurricane Isaac | High Tides
Graham MacDonald
2012-08-31 | Hurricane Isaac | High Tides
Graham MacDonald
2012-09-01 | Labor Day
2012-09-02 | Labor Day
2012-09-03 | Labor Day/ Mark and Duncan did 1st overflight since Isaac
2012-09-04 | Overflight | Overflight
| FitzGerald | Chapman
2012-09-05 | NOLA | Office
| FitzGerald | Chapman
2012-09-06 | Elmer's Island- RA | Elmer's Island- RA
| FitzGerald | Chapman
2012-09-07 | Fourchon Beach- RA | Grand Isle- RA
| FitzGerald | Chapman
2012-09-08 | Grand Terre 2- RA | N Barataria Bay- RA | Grand Terre 3- RA | West Timbalier- RA
| FitzGerald | Chapman | Kulp | MacDonald
2012-09-09 | Bay Chaland- RA | Casse- tete/ Calumet- RA | Trinity Island- RA
| FitzGerald | Kulp | MacDonald
2012-09-10 | St Bernard- KeelBoat Pass RA- LASB05-014-20 & LASB05-015-10 | N Barataria Bay- RA | Grand Terre 1- RA
| FitzGerald | Kulp | MacDonald
2012-09-11 | Western End of Grand Isle- RA | Eastern End of Elmer's Island- RA
| MacDonald | FitzGerald
2012-09-12 | Grand Terre 1, 2 and 3- re-establish beach profiles | Whiskey cancelled- Overflight requested by OPS | Cancelled due to Wx Creole Gap Key -(RA) LASB07-010-10 & LASB07-012-10
| MacDonald | FitzGerald | Ramsey
2012-09-13 | West Timbalier- (RA) LALF01-036-20, LATB04-008-10, LATB04-009-10, LATB04-010-20/ (RA) LATB04-004-10 & LATB04-010-10 | Fourchon Breach Project | Cancelled due to thunderstorms Drum Bay & Turtle Pen Isle(RA) - LASB05-017-10 LASB06-002-10
| MacDonald | FitzGerald | Ramsey
2012-09-14 | Fourchon Breach Project | Cancelled mission due to access issues Trinity Island- (RA) - LATB04-001-20 | Whiskey Island -(RA) partial on LATB03-006-10
| Kulp | MacDonald | Ramsey
2012-09-15 | Fourchon Breach Project | Canceled -Middle Ground-(RA) / team went to Fourchon Breaches and helped
| Kulp | MacDonald
2012-09-16 | Fourchon Breach Project | Fourchon Breach Project
| Kulp | MacDonald
2012-09-17 | Trained Entrix personnel to do Beach Profiles | Office | Office | Office
| FitzGerald | Kroninger | Kulp | MacDonald
2012-09-18 | Middle Ground- (RA)- LAPL10-004-90- completed southern side | Cancelled due to rough seas Whiskey Island - post storm RA | Cancelled due to rough seas Trinity Island- post storm RA
| FitzGerald | Kroninger | Ramsey
2012-09-19 | South Pass- (RA)- LAPL06-001-35, LAPL06-002-10, LAPL06-010-05 and LAPL06-010-20 (RA tier 1)- LAPL06-010-10 | Pelican Nesting Site #19- (RA)-LATB04-015-20/ Bay St Elaine-(RA tier 1)- LATB04-019-10 | Kerchimbo Bay- LASB06-013-30 Turtle Pen Isle - LASB05-018-10 | Casse Tete and Calumet Islands- (RA)- LALF01-044-30 & LALF01-045-10 (RA tier 1)- LALF01-036-10 & LALF01-037-10
| FitzGerald | Kroninger | Ramsey | Graham Macdonald
2012-09-20 | OSAT- Meeting in NOLA | Trinity Island- (RA)- LATB04-001-20/ (RA tier 1)- LATB03-007-10, LATB03-008-10 & LATB04-002-10- completed all | Creole Gap Key - (RA)- LASB07-010-10 & LASB07-012-10 & (RA tier 1)- LASB07-011-20 / Isle au Pitre (RA tier 1)- LASB07-011-10 & LASB07-014-10- completed all RA tier 1 | Whiskey Island - (RA) -partial LATB03-006-10- completed
| FitzGerald | Kroninger | Ramsey | Graham Macdonald
2012-09-21 | Elmer's Island - beach profiles | West Timbalier-(RA tier 1)-- LALF01-031-10 & LALF01-031-20 / Dredge piles remaining in LATB04-010-20 | Martin Island- (RA tier 1)- LASB06-004-10 / Door Point Lagoon- (RA tier 1)- LASB06-026-20 / Drum Bay (RA)- LASB06-002-10 | SW Pass- (RA tier 1)- LAPL05-002-20, LAPL05-003-20, LAPL05-008-10 | Grand Terre 1- (RA tier 1)- LAJF01-016-60/ Fifi Island (RA tier 1)- LAJF01-015-20/ Island behind GI-(RA tier 1) - LAJF01-004-45, LAJF01-008-10 (located by Caminada Pass)
| FitzGerald | Kroninger | Ramsey | Kulp | Graham Macdonald
2012-09-22 | East Timbalier (RA tier 1) - LALF01-040-10, LALF01-040-30, LALF01-041-30 | Fourchon Breaches for OLS or Fourchon Beach- (RA tier 1) LALF02-002-10, LALF02-002-20, LALF02-003-10, LALF02-008-10 | Bay Borbeaux- (RA tier 1-) LATB04-045-10 & LATB04-046-30 | SE Pass (RA tier 1)- LAPL07-001-20, LAPL08-002-10, LAPL08-006-20 & LAPL08-006-30
| FitzGerald | Kulp | Ramsey | Graham Macdonald
2012-09-23 | Bastian Island- (RA tier 1) LAPL01-004-10, LAPL01-005-10 and LAPL02-012-10/ Bay Chaland (RA tier 1) - LAPL01-005-30 | Calumet w/OPS or Island West of Casse-Tete (RA tier 1) - LALF01-043-10 / Calumet Island (RA)- LALF01-044-30 | Bay La Mer- (RA tier 1) LAPL01-008-40, LAPL01-009-30, LAPL01-009-50 | Grand Terre 2- (RA tier 1)- LAPL01-006-15, LAPL01-006-20, LAPL01-007-10 & LAPL01-006-10
| FitzGerald | Kulp | Ramsey | Graham Macdonald
2012-09-24 | N Barataria Bay- (RA tier 1)- LAPL01-027-30, LAPL01-052-30 & LAPL01-053-80, LAPL01-041-30 (send airboats from Myrtle Grove and crewboats from sand dollar) | Pelican Nesting Site #22- (RA tier 1) - LATB02-011-20 | GI Back Barrier and Island Behing GI (RA tier 1)- LAJF01-007-10, LAJF01-003-10 & LAJF01-004-30
| Kulp | Graham Macdonald | FitzGerald
2012-09-25 | Churn Bay- (RA tier 1)- LAJF02-019-10 & LAJF02-020-10/ Manilla- (RA tier 1)- LAJF02-031-60/ Blind Bay/ Bassa Bassa- (RA tier 1)- LAJF01-032-30 & LAJF01-033-50 | Mendicant Island- (RA tier 1)- LAJF01-022-20 & LAJF01-029-20 / Queen Bess (RA tier 1)- LDWF required- LAJF01-023-10/ Fort Livingston- (RA)-LAJF01-016-65, LAJF01-016-85 & LAJF01-016-90 (water levels too high to survey- resched for 9/30/12)
| Graham MacDonald | FitzGerald
2012-09-26 | West Timbalier- (RA)- LALF01-036-20, LATB04-010-20 (remaining seg minus the piles) | Creole Gap Key - (RA)- LASB07-010-10 & LASB07-012-10
| Graham Macdonald | FitzGerald
2012-09-27 | Pelican Island- (RA tier 1)- LAJF01-032-10, LAJF01-032-20 & LAJF01-032-40- didn’t get to segment due to lightning / Grand Terre 3- (RA)- LAPL01-008-10 | South Pass (RA)- LAPL07-004-10 (Garden Island)- didn’t get to b/c of WX/ SE Pass to verify/delineate possible tar mat that wasn't sampled on last RA survey due to lack of shovel)
| Graham Macdonald | FitzGerald
2012-09-28 | Canceled due to Wx- Whiskey Island- (RA tier 1) - LATB03-004-10 & LATB03-005-10 | Mud Lake (RA tier 1)- LAJF02-041-10, LAJF02-041-20, LAJF02-041-30, LAJF02-041-50, LAJF02-041-60, LAJF02-041-70, LAJF02-042-10, LAJF02-042-20 | N Barataria Bay- (RA)- LAPL01-052-10 (zone A), LAPL01-053-20 (zone B), LAPL01-053-30 (zone D & E), LAPL01-053-60 (zone G) & LAPL01-053-70 (zone C)- only able to do Zone C b/c airboats had to return to dock due to Wx
| Graham Macdonald | FitzGerald | Kulp
2012-09-29 | Canceled due to Wx- Andre Island- (RA tier 1)- LAJF01-014-05 & LAJF01-014-15 Beauregard Island- (RA tier 1)- LAJF01-015-10 / Bay Joyeaux- (RA tier 1)- LAJF01-021-20 | Canceled due to Wx- N Barataria Waterway- (RA tier 1)- LAJF02-052-20, LAJF02-052-30, LAJF02-063-10, LAJF02-064-10, LAJF02-063-20, LAJF02-063-30, LAJF02-040-20 | Canceled due to Wx- N Barataria Bay- (RA)- LAPL01-034-20 (zone AA), LAPL01-034-50 (zone L), LAPL01-035-40 (zone X), LAPL01-040-10 (zone AC) | Mac McCarthy coming in to calibrate w/ other TL
| Graham MacDonald | FitzGerald | Kulp
2012-09-30 | Canceled due to Wx- Elmer's Island (RA)- partial on LAJF01-001-10 / Fort Livingston- (RA)-LAJF01-016-65, LAJF01-016-85 & LAJF01-016-90 | Canceled due to Wx -SW Pass- (RA)- LAPL05-009-10- can't do S Pass b/c airboats | Canceled due to Wx- Drum Bay & Fishing Smack Bay- (RA)- LASB06-002-10 / Turtle Pen Isle- (RA)- partial LASB05-017-10 | Canceled due to Wx- Passa Loutre/ Middle Ground- (RA tier 1)- LAPL10-004-10 and partial on LAPL10-004-90
| Graham Macdonald | Kulp | Ramsey | FitzGerald
2012-10-01 | Canceled due to Wx- South Pass (RA)- LAPL07-004-10 (Garden Island)/ SW Pass- (RA)- LAPL05-009-10 | Canceled due to Wx- N Barataria Bay- (RA)- LAPL01-052-10 (zone A), LAPL01-053-20 (zone B), LAPL01-053-30 (zone D & E), LAPL01-053-60 (zone G) | Canceled due to Wx - Whiskey Island- (RA tier 1)- LATB03-004-10 & LATB03-005-10 | Canceled due to Wx Pelican Island- (RA tier 1)- LAJF01-032-10, LAJF01-032-20 & LAJF01-032-40 | Canceled due to Wx Comfort Island- (RA tier 1)- LASB05-002-10 & LASB05-003-10
| FitzGerald | Kulp | Nelson | G Macdonald/ McCarthy | Ramsey
2012-10-02 | Canceled Due to Meeting in NOLA w/OPS- Passa Loutre/ Middle Ground- (RA)- LAPL10-004-10 and partial on LAPL10-004-90 | Drum Bay - (RA)- LASB06-002-10 / Turtle Pen Isle- (RA)- partial LASB05-017-10 | Elmer's Island (RA)- partial on LAJF01-001-10 / Fort Livingston- (RA)-LAJF01-016-65, LAJF01-016-85 & LAJF01-016-90 | South Pass (RA)- LAPL07-004-10 (Garden Island) / SW Pass- (RA) - LAPL05-009-10
| FitzGerald | Nelson | G Macdonald | McCarthy
2012-10-03 | Fourchon Beach Profiles / QAQC- Last day flying home in early afternoon | N Barataria Bay- (RA)- LAPL01-052-10 (zone A), LAPL01-053-20 (zone B), LAPL01-053-30 (zone D & E), LAPL01-053-60 (zone G) , partial on LAPL01-052-30 (zone B) | N Barataria Bay- (RA)- LAPL01-034-20 (zone AA), LAPL01-034-50 (zone L), LAPL01-035-40 (zone X), LAPL01-040-10 (zone AC) and partial on LAPL01-053-70 (zone C) | Calibration w/ Graham or Jenni
| FitzGerald | Nelson | G Macdonald | McCarthy
2012-10-04 | N Barataria Bay/ Joint Inspection w/ HillCorp | N Barataria Waterway- (RA tier 1)- LAJF02-052-20, LAJF02-052-30, LAJF02-063-10, LAJF02-064-10, LAJF02-063-20, LAJF02-063-30, LAJF02-040-20 | Pelican Island- (RA tier 1)- LAJF01-032-10, LAJF01-032-20 & LAJF01-032-40
| Chapman p/u airport | Nelson | McCarthy
2012-10-05 | Passa Loutre/ Middle Ground- (RA) - LAPL10-004-10 and partial on LAPL10-004-90 | Andre Island- (RA tier 1) - LAJF01-014-05 & LAJF01-014-15 Beauregard Island- (RA tier 1)- LAJF01-015-10 / Bay Joyeaux- (RA tier 1)- LAJF01-021-20 | Comfort Island- (RA tier 1) - LASB05-002-10 & LASB05-003-10 | Whiskey Island- (RA tier 1)- LATB03-004-10 & LATB03-005-10
| Chapman | Nelson | Kulp | McCarthy
2012-10-06 | West Timbalier (S4-027.r.2) SCAT MON- LALF01-036-20 (zones 12-14)- did not meet endpts | Grand Terre 3 (S4-024) PIST- LAPL01-008-10- ALARP | South Pass- (RA tier 1)- LAPL07-001-20/ Passa Loutre | Pelican Nesting Site #19 (S4-015)- SCAT MON- LATB04-015-20 | If any remaining post storm surveys needed then will replace SCCP missions on this day.
| Chapman | Nelson | Kulp | McCarthy/ Lance
2012-10-07 | Canceled Due to Wx day before by Danos safety - N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-029-10 (P,Q,S,V) | Canceled Due to Wx day before by Danos safety Passa Loutre/ Middle Ground- (RA)- remaining surveys/ South Pass (S3-003.r.7) SIR-1- LAPL06-002-10 (COW 1 &2) | Canceled Due to Wx day before by Danos safety- Trinity Island (S4-023.r.1) SIR-1- LATB04-001-20 (5 partial, 6 all, 7 partial); SCAT Mon- LATB04-006-10; | High Tides
| Chapman | Kulp | McCarthy/ Jeremy
2012-10-08 | N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-029-10 (P,Q,S,V) and also looked at LAPL01-052-10 | Grand Isle and Elmers's Island- Beach Profile QA/QC | High Tides
| Chapman | Kulp
2012-10-09 | Passa Loutre- (RA)- LAPL10-004-90 | Grand Terre 3- Beach Profile QA/QC | High Tides
| Chapman | FitzGerald
2012-10-10 | Grand Terre 1- Beach Profile QA/QC | Office Calibration | Grand Terre 2- Beach Profile QA/QC | High Tides
| Chapman | Sergy | FitzGerald
2012-10-11 | Fourchon Beach- cont Beach Profile QA/QC | Calibrating w/ Helen | High Tides
| Chapman | Sergy
2012-10-12 | Grand Isle- Beach Profile QA/QC | Calibrating w/ Helen | High Tides
| Chapman | Sergy
2012-10-13 | Cancelled due to Rough Seas West Timbalier (S4-027.r.2) SIR-2 - LATB04-009-10 & LATB04-010-20 (SUTZ only since tides are high) | South Pass (S3-003.r.7) SIR-2- LAPL06-010-20 (COW 2,3,4 &5); SIR-2- LAPL07-004-10 (SUTZ only since tides are high) | Calibrating w/Stephane | Cancelled due to Rough Seas Trinity Island (S4-023.r.1) SIR-1- LATB04-001-20 (5 partial, 6 all, 7 partial) & SIR-1- LATB04-007-10 | Last Day of High Tides
| Chapman | FitzGerald | Sergy | Grenon
2012-10-14 | Cancelled due to Rough Seas N Barataria Bay (S4-032.r.2) SCAT MON-- LAPL01-029-20 (U); SCAT MON- LAPL01-036-30 (AB) | N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-041-10 (O) | Calibrating w/ Helen | Cancelled due to Rough Seas N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-040-10 (AC)
| Chapman | FitzGerald | Sergy | Grenon
2012-10-15 | N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-053-60 (G)- did not pass/bagasse & LAPL01-053-70 (zone C)- passed | West Timbalier (S4-027.r.2) SIR-2-LATB04-009-10 / SCAT Mon- LATB04-010-20 | Pelican Nesting Site #19 (S4-015)- SIR-2- LATB04-015-20 | Brush Island (S4-037.r.1) SIR-1- LALF01-037-10
| Ramsey | FitzGerald | Sergy | Grenon
2012-10-16 | N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-051-10 (F) & LAPL01-053-10 (F) | South Pass (S3-003.r.7) SCAT Mon- LAPL06-010-20 (COW 2,3,4 &5); SIR-2- LAPL07-004-10-partial survey | Fourchon Beach Auguring at Breach #1 w/ full SCAT team | Trinity Island (S4-023.r.1) SIR-1- LATB04-001-20 (5 partial, 6 all, 7 partial); SCAT Mon- LATB04-006-10; SIR-1- LATB04-007-10 | Debra S-B first field day
| Ramsey | FitzGerald | Sergy | Grenon
2012-10-17 | Cancelled due to high water levels- tide .5 over predicted due to S wind- N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-040-10 (AC)- rescheduled for 10/20/12 | Cancelled due to high water levels- tide .5 over predicted due to S wind- N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-035-10 & LAPL01-035-40 (both X)- rescheduled for 10/20/12 | cont. Fourchon Beach Auguring at Breach #1 w/ full SCAT team | Keelboat Pass (S4-038.r.1)- PIST- LASB05-014-20-passed & LASB05-015-10- never surveyed due to time
| Ramsey | FitzGerald | Sergy | Grenon
2012-10-18 | Creole Gap Key (S4-038.r.1)- PIST- LASB07-010-10 & LASB07-012-10 | South Pass- (S3-003.r.7)- PIST- LAPL06-001-35 (COW 5-9) & SIR-1- LAPL06-002-10 (COW 1 & 2) | cont. Fourchon Beach Auguring at Breach #1 w/ full SCAT team OR Grand Terre 3 (S4-021) SIR-1- LAPL01-008-10 | Cancelled Due to High Water Levels N Barataria Bay (S4-032.r.2) SCAT MON-- LAPL01-029-20 (U); SCAT MON- LAPL01-036-30 (AB)
| Ramsey | FitzGerald | Sergy | Grenon
2012-10-19 | Trinity Island (S4-023.r.1) SCAT Mon- LATB04-001-20 (5 partial, 6 all, 7 partial); SIR-2- LATB04-006-10; SCAT Mon- LATB04-007-10 | N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-041-10 (O)- only had to survey LITZ & LAPL01-040-10 (AC) | continue if needed- Fourchon Beach Auguring at Breach #1 w/ full SCAT team | Whiskey Island and Raccoon Island for SIR-2 closure w/ parish rep
| Ramsey | FitzGerald | Sergy | Kulp
2012-10-20 | Keelboat Pass (S4-038.r.1)- PIST- LASB05-015-10 & SIR-1- LASB05-014-20 | Brush Island (S4-037.r.1) SCAT Mon- LALF01-037-10 | N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-035-10 & LAPL01-035-40 (both X)
| Ramsey | FitzGerald | Kulp
2012-10-21 | N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-051-10 (F) & LAPL01-053-10 (F) | Office- Beach Profile Data | Office- Beach Profile Data | Tide <.7 @ noon- Manilla
| Ramsey | FitzGerald | Kulp
2012-10-22 | N Barataria Bay (S4-032.r.2) SCAT MON- LAPL01-029-20 (U); SCAT MON- LAPL01-036-30 (AB) | Cancelled due to TL leaving-South Pass- (S3-003.r.7)- PIST- LAPL06-001-35 (COW 5-9)- & SIR-1- LAPL06-002-10 (COW 1 & 2) | Cancelled due to high water levels N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-040-10 (AC) | Last Day of Low Tides
| Ramsey | FitzGerald | Kulp
2012-10-23 | Office/ Profile Data
MacDonald
2012-10-24 | West Timbalier Island QA/QC of Beach Profiles-
MacDonald
2012-10-25 | Trinity Island QA/QC of Beach Profiles
MacDonald
2012-10-26 | N Barataria Bay (S4-032.r.2) PIST- LAPL01-053-30 (zone D)- partial failed & LAPL01-053-60 (zone G)- partial passed | N Barataria Bay (S4-032.r.2) PIST-LAPL01-042-10 (zone O)- needs Tx & LAPL01-027-10 (zone N)- needs Tx
| MacDonald | Kulp | Fog starting to become factor- teams delayed 1 hr at dock
2012-10-27 | Cancelled due to small craft advisory | Cancelled due to small craft advisory | Cancelled due to small craft advisory
| MacDonald | Kulp | Kroninger
2012-10-28 | Cancelled due to small craft advisory N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-034-50 (zone L) | Fourchon Beach (S4-017) PIST- LALF02-006-10 (zones 8 & 9)- zone 8 failed | Cancelled due to small craft advisory Casse-Tete Island (S4-037.r.1) PIST- LALF01-044-10 (zones 3, 4, 5 & 6) | Cancelled due to small craft advisory Grand Terre 2 (S4-020.r.1) PIST- LAPL01-002-10 (zones 16-22) | Cancelled due to small craft advisory N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-034-20 (zone AA)
| MacDonald | Kulp | Kroninger | FitzGerald | Ramsey
2012-10-29 | Cancelled due to small craft advisory Grand Terre 2 (S4-020.r.1) PIST- LAPL01-002-10 (zones 16-22) | Cancelled due to small craft advisory N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-034-50 (zone L) & partial PIST- LAPL01-053-30 (zone D) & LAPL01-053-60 (zone G) | Cancelled due to small craft advisory Casse-Tete Island (S4-037.r.1) PIST- LALF01-044-10 (zones 3, 4, 5 & 6) & Brush Island (S4-037.r.1) SCAT Mon- LALF01-037-10 | Cancelled due to small craft advisoryTrinity Island (S4-023.r.1) SCAT Mon redo- LATB04-001-20 / PIST- LATB04-001-10 (zones 5 & 6) | Cancelled due to small craft advisory N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-034-20 (zone AA)
| MacDonald | Kulp | Kroninger | FitzGerald | Ramsey
2012-10-30 | N Barataria Bay (S4-032.r.2) SIR-2 - LAPL01-040-10 (zone AC) & SCAT Mon- LAPL01-034-50 (zone L)- both passed due to NEB | N Barataria Bay (S4-032.r.2) SIR-2-LAPL01-029-20 (U) & LAPL01-036-30 (AB)- both passed | Grand Terre 2 (S4-020.r.1) PIST- LAPL01-002-10 (zones 16-22)- passed | South Pass- (S3-003.r.7)- PIST- LAPL06-001-35 (COW 5-9)- did not survey ; SIR-1- LAPL06-002-10 (COW 1 & 2)- did partial on frontside ; SCAT Mon- LAPL06-010-20-did partial on frontside
| Nelson | Ramsey | Kroninger | FitzGerald
2012-10-31 | Turtle Pen Isle (S4-038.r.1) PIST- LASB05-017-10 (zone 2) / Drum Bay (S4-007) PIST- LASB06-002-10 (zone 2)- both passed | Keelboat Pass (S4-038.r.1) SIR-1 LASB05-014-20- never started & LASB05-015-10- completed and passed | Trinity Island (S4-023.r.1) SCAT Mon redo- LATB04-001-20 / PIST- LATB04-001-10 (zones 5 & 6)- both passed | South Pass- (S3-003.r.7)- SIR-2- LAPL07-004-10- passed / SIR-1- LAPL06-002-10 (COW 1 & 2)-passed / SCAT Mon- LAPL06-010-20- passed / PIST- LAPL06-001-35- failed
| Nelson | Ramsey | Kroninger | FitzGerald
2012-11-01 | Casse-Tete Island (S4-037.r.1) PIST- LALF01-044-10 (zones 3, 4, 5 & 6)- passed & Brush Island (S4-037.r.1) SCAT Mon- LALF01-037-10-passed | N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-035-10- failed & LAPL01-035-40 (both X)- passed | Creole Gap Key (S4-038.r.1)- SIR-1- LASB07-010-10 & LASB07-012-10- both passed
| Nelson | Ramsey | FitzGerald
2012-11-02 | N Barataria Bay (S4-032.r.2) partial PIST- LAPL01-053-60 (Zone G)- passed | N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-053-20 (Zone B)- joint agency visit to organic cove | N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-034-20 (zone AA) | N Barataria Bay (S4-032.r.2) partial PIST- LAPL01-053-30 (zone D)-portion surveyed on 10/26/12 failed
| Nelson | Ramsey | FitzGerald | Kulp
2012-11-03 | GT3 Beach Profiles | Keelboat Pass (S4-038.r.1) SIR-1 LASB05-014-20- passed due to ALARP | West Timbalier Beach Profiles | West Timbalier (S4-027.r.2) PIST- LATB04-004-10 (zones 10 & 11)- ready for SIR-1
| Nelson | Ramsey | FitzGerald | Kulp
2012-11-04 | Turtle Pen Isle (S4-038.r.1) SIR-1- LASB05-017-10- partial due to Thunderstorms | Drum Bay (S4-007) SIR-1- LASB06-002-10 (zone 2)- partial due to Thunderstorms | South Pass- (S3-003.r.7)- SIR-2- LAPL06-010-20- passed | N Barataria Bay (S4-032.r.2)- SIR-2 - LAPL01-041-10 (O)- passed due to NEB | Casse-Tete Island (S4-037.r.1) SIR-1- LALF01-044-10- passed
| Nelson | Ramsey | FitzGerald | Kulp | McCarthy
2012-11-05 | N Barataria Bay (S4-032.r.2) SIR-1 - LAPL01-053-60 (Zone G)- passed | Grand Terre 2 Beach Profiles | Trinity Island Beach Profiles | Trinity Island Beach Profiles
| Nelson | FitzGerald | Kulp | McCarthy
2012-11-06 | Grand Isle Beach Profiles- stake 12 missing | Elmer's Island Beach Profiles | Office- profile data
| Nelson | FitzGerald | Macdonald
2012-11-07 | Cancelled in field- too rough for airboats and too shallow for crewboats- West Timbalier (S4-027.r.2) SIR-1- LATB04-004-10 (zones 10 & 11)- re-scheduled | N Barataria Bay- Big Island for pre-winter assessment (Zones I & part of J) | N Barataria Bay- Big Island for pre-winter assessment (Zones M & H)
| Nelson | Chapman | Macdonald
2012-11-08 | Fourchon Beach Profiles then safety celebration at Bridgeside | Fourchon Beach Profiles then safety celebration at Bridgeside | GT1 Beach Profiles then safety celebration at Bridgeside
| Nelson | Chapman | Macdonald | Debra and Dave in for NOAA
2012-11-09 | N Barataria Bay- Big Island for pre-winter assessment (Zone W) | N Barataria Bay- Big Island for pre-winter assessment (Zones I & part of J) | Elmer's Island - deep pitting where there is suspect buried oil
| Chapman | Macdonald | Kulp
2012-11-10 | Office | Office- Beach Profile Data | Office- Beach Profile Data
| Chapman | Macdonald | Kulp
2012-11-11 | Cancelled due to small craft advisory- Grand Terre 2 (S4-020.r.1) PIST- LAPL01-002-10 (zones 23, 24 & 25) | Cancelled due to small craft advisory- -Grand Terre 2 (S4-020.r.1) PIST- LAPL01-001-10 (zones 2, 3 ,7 & 9) | Cancelled due to small craft advisory- Grand Terre 1 (S4-019.r.1) PIST-LAJF01-024-10 (zones 8, 9, 10 & 11)
| Chapman | Macdonald | Kulp
2012-11-12 | Cancelled due to small craft advisory- Grand Terre 2 (S4-020.r.1) PIST- LAPL01-001-10 (zones 2, 3 ,7 & 9) & LAPL01-002-10 (zones 23, 24 & 25- if not done on 11/11/12 | Cancelled due to small craft advisory- West Timbalier (S4-027.r.2) SIR-1- LATB04-004-10 (zones 10 & 11) | Cancelled due to small craft advisory- -Turtle Pen Isle (S4-038.r.1) partial SIR-1- LASB05-017-10 & Drum Bay (S4-007) partial SIR-1- LASB06-002-10 (zone 2) re-scheduled from 11/4/12 | Cancelled due to small craft advisory- Grand Terre 1 (S4-019.r.1) PIST-LAJF01-024-10 (zones 8, 9, 10 & 11)- if not done on 11/11/12
| Chapman | Macdonald | Kulp | FitzGerald
2012-11-13 | Cancelled due to small craft advisory- N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-034-30 (zone N)- zone K is part of segment | Cancelled due to small craft advisory- South Pass (S3-003.r.7) SIR-2- LAPL07-004-10- finish LITZ from surveys on 10/16/12 & 10/31/12 | Cancelled due to small craft advisory
| Chapman | FitzGerald | Ramsey
2012-11-14 | N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-034-50 (zone L)- passed | Snorkel SCAT- Grand Isle- partial on LAJF01-016-10
| Ramsey | Farrar
2012-11-15 | Trinity Island (S4-023.r.1) SIR-2- LATB04-001-20- did not survey & SIR-1- LATB04-001-10- passed | Cancelled in field due to rough seas- West Timbalier- PIST- LATB04-008-10 (Zones 2 & partial of 3) and & LALF01-036-20 (Zone 14) & SIR-1- LATB04-004-10 | Snorkel SCAT- Grand Isle- partial on LAJF01-016-10
| Ramsey | Kroninger | Farrar
2012-11-16 | Cancelled in field due to rough seas/shalllow landing- Grand Terre 1 (S4-019.r.1) PIST-LAJF01-024-10 (zones 8, 9, 10 & 11) | Grand Terre 2 (S4-020.r.1) PIST- LAPL01-001-10 (zones 2, 3 ,7 & 9) & LAPL01-002-10 (zones 23, 24 & 25)- zones 25 and 9 did not meet SCCP criteria and all other zones passed | Middle Ground- SCCP other- post-Isaac joint agency visit - completed | Snorkel SCAT- Grand Isle- LAJF-01-016-010 and LAJF-01-011-010 (Operation Zone 14 & 13)
| Ramsey | Kroninger | Kulp | Farrar
2012-11-17 | Turtle Pen Isle (S4-038.r.1) partial SIR-1- LASB05-017-10- did partial & Drum Bay (S4-007) partial SIR-1- LASB06-002-10 (zone 2)- not able to get to | Cancelled due to rough seas/shallow landing- Grand Terre 3 (S4-024) PIST- LAPL01-008-10- (zone 6) | South Pass- (S3-003.r.7) SCAT Mon- LAPL06-002-10- passed / SIR-2- LAPL07-004-10- not able to get to / PIST- LAPL06-001-35 (zones 5,6, 7, 8 & 9)- passed | Snorkel SCAT- Grand Isle- LAJF-01-011-010 (Operation Zone 13)
| Ramsey | Kroninger | Kulp | Farrar
2012-11-18 | N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-034-20 (zone AA)- passed | Cancelled due to rough seas Keelboat Pass (S4-038.r.1) SCAT Mon- LASB05-014-20 & LASB05-015-10 | Snorkel SCAT- Grand Isle-LAJF-01-011-010 (Operation Zone 13)
| Kulp | Kroninger | Farrar
2012-11-19 | Cancelled due to office work- Creole Gap Key (S4-038.r.1)- SCAT Mon- LASB07-010-10 & LASB07-012-10 | OLS- Fourchon Beach at breach #1/ Casse-Tete Island (S4-037.r.1) SCAT Mon- LALF01-044-10- passed / Brush Island (S4-037.r.1) SIR-2- LALF01-037-10- passed | Snorkel SCAT- Grand Isle- LAJF-01-011-010 (Operation Zone 13 and 12)
| Kulp | Kroninger | Farrar
2012-11-20 | Grand Terre 1 (S4-019.r.1) PIST-LAJF01-024-10 (zones 8, 9, 10 & 11)-all zones passed except zone 8; needs to be surveyed at lower tide & Grand Terre 3 (S4-021) PIST- LAPL01-008-10- (zone 6)- passed | Snorkel SCAT- Grand Isle- partial LAJF-01-011-010 (Operation Zone 12)
| Kroninger | Farrar
2012-11-21 | Thanksgiving Holidays
2012-11-22 | Thanksgiving Holidays
2012-11-23 | Thanksgiving Holidays
2012-11-24 | Thanksgiving Holidays |  | lime green= beach profiles/PM | yellow= office work/meetings | orange= OLS ( ops support)
2012-11-25 | Thanksgiving Holidays
2012-11-26 | Thanksgiving Holidays- Travel | Thanksgiving Holidays- Travel
| Graham Macdonald | Kulp
2012-11-27 | Cancelled Due to Wx at dock- West Timbalier- PIST- LATB04-008-10 (Zones 2 & partial of 3) and & LALF01-036-20 (Zone 14) & SIR-1- LATB04-004-10 | Cancelled Due to Wx at dock- N Barataria Bay (S4-032.r.2) SCAT Mon - LAPL01-053-60 (Zone G) | Cancelled Due to Wx at dock- N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-035-40 (zone X) | Cancelled due to Wx- Snorkel SCAT- Grand Isle
| Graham Macdonald | Nelson | Grenon | Farrar
2012-11-28 | Cancelled due to Fog- Trinity Island (S4-023.r.1) SIR-2- LATB04-001-20 & SCAT Mon- LATB04-001-10 | Cancelled due to Rough Seas- Keelboat Pass (S4-038.r.1) SCAT Mon- LASB05-014-20 & LASB05-015-10 | Cancelled due to Rough Seas- Turtle Pen Isle (S4-038.r.1) partial SIR-1- LASB05-017-10 & Drum Bay (S4-007) partial SIR-1- LASB06-002-10 (zone 2) | Creole Gap Key (S4-038.r.1)- SCAT Mon- LASB07-010-10 & LASB07-012-10- both passed | Snorkel SCAT- Grand Isle- completed a partial Snorkel SCAT in LAJF-01-010-010 (Operation Zone 12 & 11) in Grand Isle
| Graham Macdonald | Nelson | Grenon | Ramsey | Farrar
2012-11-29 | West Timbalier (S4-027.r.2)- PIST- LATB04-008-10 (Zones 2 & partial of 3) and & LALF01-036-20 (Zone 14) - did not complete due to cancelled airboats | N Barataria Bay (S4-032.r.2) SCAT Mon- LAPL01-053-60 (Zone G)- passed | West Timbalier (S4-027.r.2)- SIR-1- LATB04-004-10- passed | N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-035-40 (zone X)- passed | Snorkel SCAT- Grand Isle- completed a partial Snorkel SCAT in LAJF-01-010-010 (Operation Zone 11)
| Graham Macdonald | Nelson | Grenon | Ramsey | Farrar
2012-11-30 | Trinity Island (S4-023.r.1) SIR-2- LATB04-001-20 & SCAT Mon- LATB04-001-10- both passed | Keelboat Pass (S4-038.r.1) SCAT Mon- LASB05-014-20 & LASB05-015-10- both passed | Turtle Pen Isle (S4-038.r.1) partial SIR-1- LASB05-017-10 / Drum Bay (S4-007) partial SIR-1- LASB06-002-10 (zone 2) - both passed | South Pass- (S3-003.r.7) SIR-1- LAPL06-001-35- passed | Snorkel SCAT- Grand Isle- performed required monthly safety drills
| Graham Macdonald | Nelson | Grenon | Ramsey | Farrar
2012-12-01 | Trinity Island Beach Profiles for Dec- done | Grand Terre 3 Beach Profiles for Dec- done | Grand Terre 1(S4-019.r.1) - PIST- LAJF01-024-10 (Zone 8)- delineate sub tidal mat/ Grand Terre 1 Beach Profiles for Dec- completed both tasks and passed | N Barataria Bay (S4-032.r.2) pre winter- SCCP Other- LAPL01-034-10 (STR zones H,J & M) and LAPL01-034-30 (STR zone K) & LAPL01-036-10 & LAPL01-042-10 (STR zone T) | Snorkel SCAT- Grand Isle- completed partial Snorkel SCAT in LAJF-01-010-010 (Operation Zone 11)
| Graham Macdonald | Nelson | Grenon/ Darden | Kulp | Farrar
2012-12-02 | West Timbalier (S4-027.r.2)- PIST- LATB04-008-10 (Zones 2 & partial of 3) and & LALF01-036-20 (Zone 14) -passed | Elmer's Island (S4-025) PIST- LAJF01-004-20 (Zone 1)-failed | Fourchon Beach Profiles for Dec- done | N Barataria Bay (S4-032.r.2) SCCP Other- LAPL01-053-70 (STR zone C) & LAPL01-034-30 (STR Zone K)- half of Zone K surveyed and did not meet endpoints and all of Zone C met endpoints | Office for Beach Profile Data | Snorkel SCAT- Grand Isle-completed partial Snorkel SCAT in LAJF-01-010-010 (Operation Zone 10)
| Graham Macdonald | Nelson/McKinley | Grenon | Ramsey/Darden | Kulp | Farrar
2012-12-03 | West Timbalier Island Beach Profiles for Dec | Cancelled Due to High Wave Action- Casse-Tete Island (S4-037.r.1) SIR-2- LALF01-044-10 | Elmer's Island Beach Profiles for Dec- did profiles 1-10 / 11 & 12 still need to be done for Dec | Cancelled Due to Broken Down Gatortail- South Pass- (S3-003.r.7) SIR-2- LAPL06-002-10 & LAPL07-004-10 | Snorkel SCAT- Grand Isle-completed partial Snorkel SCAT in LAJF-01-010-010 (Operation Zone 10)
| Graham Macdonald | Nelson | McCarthy | Kulp/Darden | Farrar
2012-12-04 | Grand Isle Beach Profiles for Dec | Grand Terre 2 Beach Profiles for Dec | Grand Isle Beach Profiles for Dec | N Barataria Bay (S4-032.r.3) SCCP Other- (STR Zone K remaining # 1-12) | Profile Data | Snorkel SCAT- Grand Isle
| Graham Macdonald | Nelson | McCarthy | Ramsey | Macdonald | Farrar
2012-12-05 | Cancelled Due to Thunderstorms-West Timbalier (S4-027.r.2)- SIR-1- LALF01-036-20 | Cancelled Due to Thunderstorms- Casse-Tete Island (S4-037.r.1) SIR-2- LALF01-044-10 | Elmer's Island Beach Profiles 11 and 12- done | Office Day for N Barataria Bay Pre-Winter Assessment | Office Day- Possible Snorkel SCAT locations | Cancelled Due to Thunderstorms-Snorkel SCAT- Grand Isle
| Graham Macdonald | Nelson | McCarthy | Ramsey | Macdonald | Farrar
2012-12-06 | Telepresence Meeting in NOLA from 10am-12pm |  |  |  |  | Snorkel SCAT- Grand Isle-completed a partial Snorkel SCAT in LAJF-01-010-010 and moved into LAJF 01-10-15 (both in Operation Zone 10)
| Graham Macdonald | Nelson | McCarthy | Ramsey | Macdonald | Farrar
2012-12-07 | West Timbalier (S4-027.r.2)- SIR-1- LALF01-036-20- failed | Casse-Tete Island (S4-037.r.1) SIR-2- LALF01-044-10- passed | Fourchon Beach (S4-017) PIST- LALF02-006-10 (zones 7 and 8)- passed | N Barataria Bay (S4-032.r.3) PIST- LAPL01-036-10 (Zone T)-passed & LAPL01-029-10 (Zone Q)- passed | N Barataria Bay (S4-032.r.3) PIST- LAPL01-053-20 (Zone B)-failed &LAPL01-035-10 (Zone X)- passed | Snorkel SCAT- Grand Isle completed a partial Snorkel SCAT in LAJF 01-10-15 (Operation Zone 10)
| Graham Macdonald | Nelson | McCarthy | Kulp | Macdonald | Farrar
2012-12-08 | Casse-Tete Island- Re-establish PM site #'s 35, 39 and 40 | N Barataria Bay- Re-establish PM site #'s 5, 6, 10, 11, 13 and 24 | Calumet Island (S4-035) PIST- LALF01-044-30 (Zone 1, 2 & 3)-passed | N Barataria Bay (S4-032.r.3) PIST- LAPL01-027-10 (Zone N)-failed | N Barataria Bay (S4-032.r.3) PIST-LAPL01-042-10 (Zone O) -passed | Snorkel SCAT- Grand Isle-completed a partial Snorkel SCAT in LAJF 01-10-15 (Operation Zone 10 & 9)
| Graham Macdonald | Nelson | McCarthy | Kulp | Macdonald | Farrar
2012-12-09 | Office | Office | Office | Office | Snorkel SCAT- Grand Isle
| Macdonald | Nelson | McCarthy | Kulp | Farrar
2012-12-10 | All Vessel Missions Cancelled Due to Incoming Cold Front on Friday, Dec 7th | All Vessel Missions Cancelled Due to Incoming Cold Front on Friday, Dec 7th | Grand Isle Beach Profiles Redo #'s 1- 5 | All Vessel Missions Cancelled Due to Incoming Cold Front on Friday, Dec 7th | All Vessel Missions Cancelled Due to Incoming Cold Front on Friday, Dec 7th | Cancelled due to Wx- Snorkel SCAT- Grand Isle
| Macdonald | Nelson | McCarthy | Kulp | Ramsey | Farrar
2012-12-11 | N Barataria Bay (S4-032.r.3) SIR-1- LAPL01-029-10 (zones P,Q,S & V)-completed 1/3 of segment & partial PIST- LAPL01-036-10 (Zone T)- passed | Fourchon Beach (S4-017) SIR-1- LALF02-006-10- Zone 9 failed | Cancelled Due to Small Craft Advisory- South Pass- (S3-003.r.7) SIR-2- LAPL06-002-10 & LAPL07-004-10 | Keelboat Pass (S4-038.r.1) SIR-2- LASB05-014-20 - passed & LASB05-015-10- never surveyed due to time | Snorkel SCAT- Grand Isle-continued survey of LAJF 01-10-15 / zone 9.
| Chapman | McCarthy | Kulp | Ramsey | Farrar
2012-12-12 | Cancelled Night Before Due to Wx- N Barataria Bay (S4-032.r.2) SIR-2- LAPL01-053-60 (Zone G) | Cancelled Night Before Due to Wx-Creole Gap Key (S4-038.r.1)- SIR-2- LASB07-010-10 & LASB07-012-10 | Cancelled Night Before Due to Wx-Calumet Island (S4-035) SIR-1- LALF01-044-30 | Cancelled Night Before Due to Wx-N Barataria Bay (S4-032.r.2) SIR-1 LAPL01-035-10 (Zone X) | Snorkel SCAT- Grand Isle-did not complete any work due to low water temps
| Chapman | Ramsey | McCarthy | Kulp | Farrar
2012-12-13 | N Barataria Bay (S4-032.r.3) PIST- LAPL01-053-70 (zone C) - passed & PIST- LAPL01-053-30 (zone D) -passed & SIR-2- LAPL01-053-60 (Zone G)-passed | N Barataria Bay (S4-032.r.3) SIR-1- LAPL01-042-10 (zones O & T)- passed | West Timbalier (S4-027.r.2)- SCAT Mon- LATB04-004-10- passed/ PM site #42 re-established | South Pass- (S3-003.r.7) SIR-2- LAPL06-002-10- passed /SIR-2- LAPL07-004-10- did not start due to time | Creole Gap Key (S4-038.r.1)- SIR-2- LASB07-010-10 & LASB07-012-10- partial survey on both segs due to no airboats-both passed
| Chapman | Kroninger | McCarthy | Kulp | Ramsey
2012-12-14 | N Barataria Bay (S4-032.r.3) partial SIR-1- LAPL01-029-10 (zones P,Q,S & V)- passed & SIR-1 LAPL01-035-10 (Zone X)- passed | Keelboat Pass (S4-038.r.1) SIR-2- LASB05-015-10- did not start due to access issues | Calumet Island (S4-035) SIR-1- LALF01-044-30- passed | South Pass- (S3-003.r.7) SCAT Mon- LAPL06-001-35- did not start due to time & SIR-2- LAPL07-004-10- passed (NCP pending)
| Chapman | Kroninger | McCarthy | Kulp
2012-12-15 | N Barataria Bay (S4-032.r.3) SIR-1- LAPL01-053-70 ( C)- passed | Turtle Pen Isle (S4-038.r.1) SCAT Mon- LASB05-017-10- passed | Trinity Island (S4-023.r.1) SIR-2- LATB04-001-10- passed (NCP pending) | Office Day
| Chapman | Kroninger | McCarthy | Kulp
2012-12-16 | N Barataria Bay (S4-032.r.2) SIR-1- LAPL01-036-10 (zones R,T,Y & Z)- passed | N Barataria Bay (S4-032.r.3) SIR-1- LAPL01-053-30 (D & E)- passed | Grand Terre 3- PM site #'s 25,26 & 30 | South Pass- (S3-003.r.7) SCAT Mon- LAPL06-001-35- passed | Creole Gap Key (S4-038.r.1)-cont. SIR-2- LASB07-010-10 & LASB07-012-10- passed
| Chapman | Kroninger | McCarthy | Kulp | Ramsey
2012-12-17 | Cancelled Due to Thunderstorms- Calumet 43 and West Timbalier 49,51 PM | Cancelled Due to Thunderstorms - Drum Bay (S4-007) SCAT Mon- LASB06-002-10 | Cancelled Due to Thunderstorms- Keelboat Pass (S4-038.r.1) SIR-2- LASB05-015-10 | Office
| Chapman | Kroninger | Ramsey | Kulp
2012-12-18 | PM- Calumet 43 and West Timbalier 49 & 51 | Drum Bay (S4-007) SCAT Mon- LASB06-002-10- completed big island | Keelboat Pass (S4-038.r.1) SIR-2- LASB05-015-10- failed | Grand Terre 1 Beach Profiles for Dec
| Chapman | Kroninger | Ramsey | Kulp
2012-12-19 | Cancelled Day Before Due to Lack of Work | Cancelled Day Before Due to Lack of Work | Grand Terre 3 (S4-024) PIST- LAPL01-008-10 (zones 1 & 2)-passed & Fourchon Beach (S4-017) PIST- LALF02-006-10 (zone 9)-passed | Office Day
| Chapman | Kroninger | Ramsey | Kulp
2012-12-20 | Cancelled Due to Inclement Wx | Cancelled Due to Inclement Wx | Cancelled Due to Inclement Wx | Office Day
| Chapman | Kroninger | Ramsey | Kulp | Debra S-B/Dave/Travis last field day

## Tides 2013
| Timbalier |  | Caminada Pass |  | Barataria Bay |  | GT2 |  | SW Pass |  | St. Bernard
2013-04-15 |  |  |  |  | 8:00a | 3 hr 11 min
2013-04-16 |  |  |  |  | 8:00a | 4 hr 1 min
2013-04-17 |  |  |  |  | 8:00a | 4 hr 53 min
2013-04-18 |  |  |  |  | 8:00a | 5 hr 50 min
2013-04-19 |  |  |  |  | 8:00a | 7 hr 0 min
2013-04-20 |  |  |  |  | 8:00a | 7 hr 0 min
2013-04-21 |  |  |  |  | 8:00a | 7 hr 0 min
2013-04-22 |  |  |  |  | 8:00a | 7 hr 0 min
2013-04-23
2013-04-24
2013-04-25
2013-04-26
2013-04-27
2013-04-28
2013-04-29 |  |  |  |  | 8:00a | 2 hr 9 min
2013-04-30 |  |  |  |  | 8:00a | 3 hr 9 min
2013-05-01 |  |  |  |  | 8:00a | 4hr 30 min
2013-05-02 |  |  |  |  | 8:00a | 5 hr 17 min
2013-05-03 |  |  |  |  | 8:00a | 6 hr 52 min
2013-05-04 |  |  |  |  | 8:00a | 7 hr 0 min
2013-05-05
2013-05-06
2013-05-07
2013-05-08
2013-05-09
2013-05-10
2013-05-11
2013-05-12
2013-05-13
2013-05-14 |  |  |  |  | 8:00a | 2 hr 38 min
2013-05-15 |  |  |  |  | 8:00a | 3 hr 23 min
2013-05-16 |  |  |  |  | 8:00a | 4 hr 11 min
2013-05-17 |  |  |  |  | 8:00a | 5 hr 12 min
2013-05-18 |  |  |  |  | 8:00a | 7 hr 0 min
2013-05-19 |  |  |  |  | 8:00a | 7 hr 0 min
2013-05-20
2013-05-21
2013-05-22
2013-05-23
2013-05-24
2013-05-25
2013-05-26
2013-05-27
2013-05-28 |  |  |  |  | 8:00a | 2 hr 28 min
2013-05-29 |  |  |  |  | 8:00a | 3 hr 31 min
2013-05-30 |  |  |  |  | 8:00a | 4 hr 47 min
2013-05-31 |  |  |  |  | 8:00a | 7 hr 0 min
2013-06-01 |  |  |  |  | 8:00a | 7 hr 0 min
2013-06-02 |  |  | 1:00p | 2 hr 0 min
2013-06-03
2013-06-04
2013-06-05
2013-06-06
2013-06-07
2013-06-08
2013-06-09
2013-06-10
2013-06-11 |  |  |  |  | 8:00a | 2 hr 21 min
2013-06-12 |  |  |  |  | 8:00a | 3 hr 3 min
2013-06-13 |  |  |  |  | 8:00a | 3 hr 56 min
2013-06-14 |  |  |  |  | 8:00a | 5 hr 26 min
2013-06-15 |  |  |  |  | 8:00a | 7 hr 0 min
2013-06-16 |  |  |  |  | 8:00a | 7 hr 0 min
2013-06-17 |  |  | 11:56a | 3 hr 4 min | 8:00a | 7 hr 0 min
2013-06-18 |  |  | 12:18p | 2 hr 42 min | 12:49p | 2 hr 11 min |  |  | 12:09p | 2 hr 51 min
2013-06-19 |  |  | 12:55p | 2 hr 5 min |  |  |  |  | 12:06p | 2 hr 54 min
2013-06-20 | [8 empty] | 12:37p | 2 hr 23 min
2013-06-21
2013-06-22
2013-06-23
2013-06-24
2013-06-25
2013-06-26 |  |  |  |  | 8:00a | 3 hr 9 min
2013-06-27 |  |  |  |  | 8:00a | 4 hr 52 min
2013-06-28 |  |  |  |  | 8:00a | 7 hr 0 min
2013-06-29 |  |  | 11:31a | 3 hr 29 min | 8:00a | 7 hr 0 min
2013-06-30 | 12:26p | 2 hr 34 min | 11:15a | 3 hr 45 min |  |  |  |  | 12:12p | 2 hr 48 min
2013-07-01 | 12:36p | 2 hr 24 min | 11:55a | 3 hr 5 min | 12:26p | 2 hr 34 min |  |  | 11:45a | 3 hr 15 min
2013-07-02 |  |  | 12:34p | 2 hr 26 min |  |  |  |  | 12:01p | 2 hr 59 min
2013-07-03 | [8 empty] | 12:31p | 2 hr 29 min
2013-07-04
2013-07-05
2013-07-06
2013-07-07
2013-07-08
2013-07-09
2013-07-10 |  |  |  |  | 8:00a | 2 hr 23 min
2013-07-11 |  |  |  |  | 8:00a | 3 hr 17 min
2013-07-12 |  |  |  |  | 8:00a | 5 hr 3 min
2013-07-13 |  |  |  |  | 8:00a | 7 hr 0 min
2013-07-14 |  |  | 11:42a | 3 hr 18 min | 8:00a | 7 hr 0 min
2013-07-15 | 12:15p | 2 hr 45 min | 10:54a | 4 hr 6 min |  |  | 1:00p | 3 hr | 12:27p | 2 hr 33 min
2013-07-16 | 12:14p | 2 hr 46 min | 11:23a | 3 hr 37 min | 12:04p | 2 hr 56 min | 1:00p | 3 hr | 10:58a | 4 hr 2 min
2013-07-17 | 12:39p | 2 hr 21 min | 12:08p | 2 hr 52 min |  |  | 1:00p | 3 hr | 11:03a | 3 hr 57 min
2013-07-18 |  |  | 12:57p | 2 hr 3 min |  |  |  |  | 11:43a | 3 hr 17 min
2013-07-19 | [8 empty] | 12:19p | 2 hr 41 min
2013-07-20
2013-07-21
2013-07-22
2013-07-23
2013-07-24 |  |  |  |  | 8:00a | 2 hr 1 min
2013-07-25 |  |  |  |  | 8:00a | 3 hr 43 min
2013-07-26 |  |  |  |  | 8:00a | 7 hr 0 min
2013-07-27 |  |  | 11:37a | 3 hr 23 min | 8:00a | 7 hr 0 min
2013-07-28 | 12:13p | 2 hr 47 min | 10:42a | 4 hr 18 min | 10:23a | 4 hr 37 min | 1:00p | 3 hr | 11:27a | 3 hr 33 min
2013-07-29 | 12:18p | 2 hr 42 min | 11:17a | 3 hr 43 min | 11:58a | 3 hr 2 min | 1:00p | 3 hr | 10:47a | 4 hr 13 min
2013-07-30 | 12:47p | 2 hr 13 min | 12:06p | 2 hr 54 min | 12:57p | 2 hr 3 min |  |  | 11:10a | 3 hr 50 min
2013-07-31 |  |  | 12:53p | 2 hr 7 min |  |  |  |  | 11:45a | 3 hr 15 min
2013-08-01 | [8 empty] | 12:21p | 2 hr 39 min
2013-08-02
2013-08-03
2013-08-04
2013-08-05
2013-08-06
2013-08-07
2013-08-08
2013-08-09 |  |  |  |  | 8:00a | 2 hr 18 min
2013-08-10 |  |  |  |  | 8:00a | 7 hr 0 min
2013-08-11 |  |  |  |  | 9:46a | 5 hr 14 min
2013-08-12 |  |  | 11:10a | 3 hr 50 min | 11:01a | 3 hr 59 min
2013-08-13 | 12:14p | 2 hr 46 min | 11:13a | 3 hr 47 min | 12:04p | 2 hr 56 min | 1:00p | 3 hr | 10:28a | 4 hr 32 min
2013-08-14 | 12:34p | 2 hr 26 min | 11:53a | 3 hr 7 min |  |  | 1:00p | 3 hr | 10:34a | 4 hr 26 min
2013-08-15 |  |  | 12:43p | 2 hr 17 min |  |  | 12:43p | 2 hr 17 min | 11:13a | 3 hr 47 min
2013-08-16 | [8 empty] | 11:53a | 3 hr 7 min
2013-08-17 | [8 empty] | 12:52p | 2 hr 8 min
2013-08-18
2013-08-19
2013-08-20
2013-08-21
2013-08-22
2013-08-23 |  |  |  |  | 8:50a | 4 hr 4 min
2013-08-24 |  |  |  |  | 10:07a | 4 hr 53 min
2013-08-25 |  |  | 11:48a | 2 hr 19 min | 10:59a | 4 hr 1 min
2013-08-26 |  |  | 11:32a | 3 hr 28 min | 12:03p | 2 hr 57 min
2013-08-27 |  |  | 12:16p | 2 hr 44 min | 12:57p | 2 hr 3 min |  |  | 11:28a | 3 hr 32 min
2013-08-28 | [8 empty] | 11:49a | 3 hr 11 min
2013-08-29 | [8 empty] | 12:34p | 2 hr 26 min
2013-08-30
2013-08-31
2013-09-01
2013-09-02
2013-09-03
2013-09-04
2013-09-05
2013-09-06
2013-09-07
2013-09-08 |  |  |  |  | 10:53a | 4 hr 7 min
2013-09-09 |  |  |  |  | 11:13a | 3 hr 47 min
2013-09-10 | 12:21p | 2 hr 37 min | 11:00a | 4 hr 0 min | 11:51a | 3 hr 9 min
2013-09-11 | 12:26p | 2 hr 34 min | 11:35a | 3 hr 25 min | 12:46p | 2 hr 14 min |  |  | 10:26a | 4 hr 16 min
2013-09-12 |  |  | 12:19p | 2 hr 41 min |  |  |  |  | 11:02a | 3 hr 58 min
2013-09-13 | [8 empty] | 12:00p | 3 hr 0 min
2013-09-14
2013-09-15
2013-09-16
2013-09-17
2013-09-18
2013-09-19
2013-09-20
2013-09-21 |  |  |  |  | 9:56a | 5 hr 4 min
2013-09-22 |  |  |  |  | 10:25a | 4 hr 35 min
2013-09-23 |  |  | 11:05a | 2 hr 20 min | 11:16a | 3 hr 44 min
2013-09-24 |  |  | 11:42a | 3 hr 1 min | 12:13p | 2 hr 47 min
2013-09-25 |  |  | 12:58p | 2 hr 2 min
2013-09-26
2013-09-27
2013-09-28
2013-09-29
2013-09-30
2013-10-01
2013-10-02
2013-10-03
2013-10-04
2013-10-05 |  |  |  |  | 9:04a | 5 hr 34 min
2013-10-06 |  |  | 9:01a | 2 hr 0 min | 9:02a | 5 hr 58 min
2013-10-07 | 9:44a | 2 hr 56 min | 8:33a | 5 hr 12 min | 9:34a | 5 hr 26 min
2013-10-08 | 9:54a | 4 hr 44 min | 9:03a | 5 hr 57 min | 10:24a | 4 hr 36 min | 10:28a | 3 hr 58 min
2013-10-09 | 10:33a | 4 hr 27 min | 9:42a | 5 hr 18 min | 11:13a | 3 hr 47 min | 11:07a | 3 hr 53 min
2013-10-10 | 11:30a | 3 hr 30 min | 10:39a | 4 hr 21 min | 12:10p | 2 hr 50 min | 12:14p | 2 hr 46 min
2013-10-11 | 12:54p | 2 hr 6 min | 11:53a | 3 hr 7 min
2013-10-12
2013-10-13
2013-10-14
2013-10-15
2013-10-16
2013-10-17 |  |  |  |  | 8:00a | 4 hr 39 min
2013-10-18 |  |  |  |  | 8:00a | 7 hr 0 min
2013-10-19 |  |  | 8:00a | 3 hr 59 min | 8:00a | 7 hr 0 min
2013-10-20 | 8:12a | 4 hr 21 min | 8:00a | 5 hr 30 min | 8:22a | 6 hr 38 min | 8:56a | 3 hr 12 min
2013-10-21 | 8:40a | 5 hr 4 min | 8:00a | 6 hr 33 min | 9:00a | 6 hr 0 min | 9:24a | 4 hr 6 min
2013-10-22 | 9:26a | 5 hr 8 min | 8:35a | 6 hr 25 min | 9:46a | 5 hr 14 min | 10:10a | 4 hr 11 min
2013-10-23 | 10:21a | 4 hr 39 min | 9:20a | 5 hr 40 min | 10:31a | 4 hr 29 min | 10:55a | 3 hr 58 min
2013-10-24 | 11:24a | 3 hr 36 min | 10:13a | 4 hr 47 min | 11:24a | 3 hr 36 min | 12:08p | 2 hr 52 min
2013-10-25 | 12:34p | 2 hr 26 min | 11:13a | 3 hr 47 min | 12:04p | 2 hr 56 min
2013-10-26 |  |  | 12:20p | 2 hr 40 min | 12:51p | 2 hr 9 min
2013-10-27
2013-10-28
2013-10-29
2013-10-30
2013-10-31 |  |  |  |  | 8:00a | 5 hr 36 min
2013-11-01 |  |  |  |  | 8:00a | 7 hr 0 min
2013-11-02 | 8:00a | 3 hr 25 min | 8:00a | 4 hr 18 min | 8:00a | 7 hr 0 min | 8:00a | 3 hr 12 min
2013-11-03 | 8:00a | 4 hr 18 min | 8:00a | 4 hr 53 min | 8:00a | 7 hr 0 min | 8:00a | 4 hr 27 min
2013-11-04 | 8:00a | 5 hr 40 min | 8:00a | 6 hr 7 min | 8:00a | 7 hr 0 min | 8:00a | 5 hr 58 min
2013-11-05 | 8:00a | 6 hr 48 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-06 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-07 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:40a | 6 hr 20 min | 8:24a | 6 hr 36 min
2013-11-08 | 8:34a | 6 hr 26 min | 8:00a | 7 hr 0 min | 9:24a | 5 hr 36 min | 9:18a | 5 hr 42 min
2013-11-09 | 9:30a | 5 hr 30 min | 8:49a | 6 hr 11 min | 10:10a | 4 hr 50 min | 10:24a | 4 hr 36 min
2013-11-10 | 10:59a | 4 hr 1 min | 9:48a | 5 hr 12 min | 10:39a | 4 hr 21 min | 11:43a | 3 hr 17 min
2013-11-11 |  |  | 11:12a | 3 hr 40 min | 10:33a | 4 hr 27 min
2013-11-12 |  |  |  |  | 8:00a | 7 hr 0 min
2013-11-13 |  |  |  |  | 8:00a | 7 hr 0 min
2013-11-14 | 8:00a | 2 hr 38 min | 8:00a | 3 hr 51 min | 8:00a | 7 hr 0 min | 8:00a | 2 hr 25 min
2013-11-15 | 8:00a | 4 hr 9 min | 8:00a | 4 hr 52 min | 8:00a | 7 hr 0 min | 8:00a | 4 hr 23 min
2013-11-16 | 8:00a | 5 hr 9 min | 8:00a | 5 hr 45 min | 8:00a | 7 hr 0 min | 8:00a | 5 hr 32 min
2013-11-17 | 8:00a | 6 hr 0 min | 8:00a | 6 hr 33 min | 8:00a | 7 hr 0 min | 8:00a | 6 hr 27 min
2013-11-18 | 8:00a | 6 hr 46 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-19 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-20 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-21 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-22 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-11-23 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:31a | 6 hr 29 min
2013-11-24 | 8:05a | 6 hr 55 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 9:03a | 5 hr 57 min
2013-11-25 | 8:28a | 6 hr 32 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 9:32a | 5 hr 28 min
2013-11-26 | 8:50a | 6 hr 10 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 9:54a | 5 hr 6 min
2013-11-27 | 8:00a | 5 hr 17 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 9:12a | 2 hr 50 min
2013-11-28 | 8:00a | 4 hr 12 min | 8:00a | 5 hr 37 min | 8:00a | 7 hr 0 min | 8:00a | 4 hr 13 min
2013-11-29 | 8:00a | 4 hr 35 min | 8:00a | 5 hr 25 min | 8:00a | 7 hr 0 min | 8:00a | 5 hr 0 min
2013-11-30 | 8:00a | 5 hr 17 min | 8:00a | 5 hr 51 min | 8:00a | 7 hr 0 min | 8:00a | 5 hr 53 min
2013-12-01 | 8:00a | 6 hr 6 min | 8:00a | 6 hr 33 min | 8:00a | 7 hr 0 min | 8:00a | 6 hr 46 min
2013-12-02 | 8:00a | 6 hr 58 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-03 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-04 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-05 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-06 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-07 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-08 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-09 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-10 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-11 | 8:00a | 6 hr 1 min | 8:00a | 6 hr 54 min | 8:00a | 7 hr 0 min | 8:00a | 6 hr 44 min
2013-12-12 | 8:00a | 5 hr 56 min | 8:00a | 6 hr 36 min | 8:00a | 7 hr 0 min | 8:00a | 6 hr 43 min
2013-12-13 | 8:00a | 6 hr 18 min | 8:00a | 6 hr 52 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-14 | 8:00a | 6 hr 53 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-15 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-16 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-17 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-18 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-19 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-20 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-21 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-22 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-23 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-24 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-25 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-26 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-27 | 8:00a | 6 hr 25 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-28 | 8:00a | 6 hr 24 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-29 | 8:00a | 6 hr 51 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-30 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min
2013-12-31 | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min | 8:00a | 7 hr 0 min